## Product Roadmap
Workstream | Now | Next | Later
ENGINEERING | MoTeC parsers complete — 70 channels decode (raw×mul/10^dec+shift) | Clerk JWT + role claims at API | 2nd sim title: iRacing / ACC (new ingest only)
| FastAPI + async SQLAlchemy scaffold; 14-table ORM | get_db() SET LOCAL RLS tenant context | Live streaming telemetry (not post-session)
| Telemetry dashboard + 70-channel traces (prototyped) | Agent orchestration moved server-side | Setup recommendation engine (Optimizer writes params)
| Phase 1 deploy: Vercel/Netlify + Railway/Render/Fly | Cost levers: tiering + caching + metering | Voice-coach bridge / local companion app
| TimescaleDB hypertable conversion (at deploy) | Session notes (driver + agent-tagged) | Corner-by-corner vs published ideal
| Sanitized .ld fixture + GitHub push | Garage accounts (2–50 seats, pooled quota)
MANAGEMENT | Working Plan + Product Phase Plan v1.0 | Quota / metering enforcement live | Product analytics + churn signals
| Clean Agile cadence (INVEST, AC-as-DoD) | Garage admin dashboards wired to real perms | Content ops for corner-dossier library
| TDD lap-analysis suite (128 backend tests) | Support workflow + issue queue | Code Craft gating on merge (blocks majors)
| Code Craft standards auditor (prototype) | Onboarding funnel instrumentation
BUSINESS | Positioning: engineer the car, not coach the driver | Plan tiers Rookie → Paddock + Stripe billing | Paddock B2B / league pilots
| Competitor map (Track Titan, Trophi.ai, RaceLab) | Usage credits priced 3–7× cost | Pricing experiments (run-class credits)
| AI cost model — ~$0.04/$0.18/$0.26 per run class | Per-user margin visibility | Premium live/voice coaching tier
Setup marketplace
Direction | Launch a telemetry product first; switch on intelligence once revenue exists; expand to new titles last. Defer cost and complexity until the prior phase justifies them.

## OKR
Period |  | Q3 2026 (post-Phase-0)
Team |  | ByteCraft Racing
Owner |  | Ohioma
1 | O1 — Ship a telemetry product a solo driver will pay for (Phase 1 launch)
Key Result |  | Baseline | Target | Current | Conf. % | Status
Register → dashboard time |  | n/a | <2 min | not deployed | 60% | On track
Upload → full session view |  | n/a | <10 s | 10 s (local) | 70% | On track
70 channels decoded & flagged |  | 0 | 70 | 70 (2 flagged) | 95% | Done
Trend across ≥2 sessions |  | none | best-lap chart | prototyped | 65% | On track
Uptime over first 30 days |  | n/a | 99% | not live | 50% | At risk
2 | O2 — Make the Race Engineering Agent real and economical (server-side)
Key Result |  | Baseline | Target | Current | Conf. % | Status
Standard run end-to-end server-side |  | client-side | <60 s + cost logged | client prototype | 55% | At risk
Specialists never on Opus (invariant) |  | — | test green in CI | test exists | 80% | On track
Cached-input share on repeat run |  | 0% | ≥60% | not wired | 45% | At risk
Cost vs naive all-Opus baseline |  | $0.95/run | ~90% lower | modeled | 70% | On track
3 | O3 — Establish a trustworthy multi-tenant foundation
Key Result |  | Baseline | Target | Current | Conf. % | Status
JWT role claims gate every route |  | client-side only | 100% of routes | not started | 40% | At risk
Cross-tenant read at DB layer |  | app WHERE | impossible (RLS) | SQL written | 55% | On track
Garage pooled quota accuracy |  | none | accurate aggregation | prototyped | 50% | On track
Quota blocks the N+1 run |  | none | enforced + upgrade path | metering built | 60% | On track
4 | O4 — Validate unit economics and pricing
Key Result |  | Baseline | Target | Current | Conf. % | Status
Per-user margin visible |  | none | 1-screen cost vs revenue | modeled | 45% | At risk
Plan tiers live with billing |  | none | Rookie→Paddock + Stripe | planned | 35% | At risk
Usage credits priced 3–7× cost |  | none | credit layer live | designed | 40% | At risk
Paddock B2B / league pilot |  | 0 | ≥1 signed | not started | 25% | At risk

## IMS
Project | ByteCraft Racing — Race Engineering Manager |  |  | Baseline Date |  | 30 Jun 2026
PM | Ohioma
ID | MILESTONE/TASKS |  | OWNER | START | FINISH | %COMP | STATUS
M0 | PHASE 0 — PROTOTYPING |  | Ohioma/ByteCraft | May 2026 | 30 Jun 2026 | 95% | ACTIVE
0.1 | MoTeC .ld/.ldx/.svm decode (70 channels) |  | ByteCraft | May 2026 | 30 Jun 2026 | 100% | DONE
0.2 | Agent prototypes v2 → v12 (live API) |  | Claude/ByteCraft | May 2026 | Jun 2026 | 100% | DONE
0.3 | AI cost model + metering service (30+ tests) |  | Ohioma | Jun 2026 | Jun 2026 | 100% | DONE
0.4 | 14-table ORM + ERD (FK integrity) |  | ByteCraft | Jun 2026 | Jun 2026 | 100% | DONE
0.5 | Sanitized .ld fixture + GitHub push |  | ByteCraft | Jul 2026 | — | 0% | LATE
M1 | PHASE 1 — LAUNCH (telemetry only) |  | Ohioma/ByteCraft | Jul 2026 | TBD | 10% | ACTIVE
1.1 | Wire frontend to backend API |  | ByteCraft | Jul 2026 | — | 0% | HOLD
1.2 | Deploy hosting + Postgres |  | ByteCraft | — | — | 0% | HOLD
1.3 | TimescaleDB hypertable conversion |  | ByteCraft | — | — | 0% | HOLD
1.4 | Cross-session trend / progression view |  | ByteCraft | — | — | 40% | ACTIVE
1.5 | Sentry / error tracking; 99% uptime target |  | ByteCraft | — | — | 0% | HOLD
M2 | PHASE 2 — INTELLIGENCE + TEAMS |  | Ohioma/ByteCraft | TBD | TBD | 5% | HOLD
2.1 | Clerk JWT + role claims (critical path) |  | ByteCraft | — | — | 0% | HOLD
2.2 | get_db() SET LOCAL RLS tenant context |  | ByteCraft | — | — | 0% | HOLD
2.3 | Agent orchestration server-side |  | ByteCraft/Claude | — | — | 0% | HOLD
2.4 | Cost levers enforced (tier/cache/meter) |  | ByteCraft | — | — | 30% | HOLD
2.5 | Garage accounts + invite + pooled quota |  | ByteCraft | — | — | 0% | HOLD
2.6 | Session notes (driver + agent-tagged) |  | ByteCraft | — | — | 0% | HOLD
2.7 | Stripe plan tiers (Rookie → Paddock) |  | Ohioma | — | — | 0% | HOLD
M3 | PHASE 3 — MANAGEMENT |  | Ohioma | TBD | TBD | 0% | HOLD
3.1 | Admin usage/cost dashboards; per-user margin |  | ByteCraft | — | — | 0% | HOLD
3.2 | Corner-dossier publishing pipeline |  | Ohioma | — | — | 0% | HOLD
3.3 | Onboarding funnel + support workflow |  | ByteCraft | — | — | 0% | HOLD
3.4 | Code Craft in CI (blocks majors) |  | ByteCraft | — | — | 0% | HOLD
M4 | PHASE 4 — EXPANSION |  | Ohioma | TBD | TBD | 0% | HOLD
4.1 | Second sim title (iRacing / ACC) |  | ByteCraft | — | — | 0% | HOLD
4.2 | Live/streaming telemetry + voice tier |  | ByteCraft | — | — | 0% | HOLD
ACTIVE |  | DELAY | HOLD |  | LATE

## RACI
Project | ByteCraft Racing — Race Engineering Manager |  |  | Baseline Date |  | 30 Jun 2026
PM | Ohioma
|  |  | PMO / Product (Ohioma) | Engineering (ByteCraft Co.) | AI Build+Runtime (Claude) | QA / Acceptance | Sponsor (Axiom Black) | —
Deliverable
Product / Phase Plan & roadmap |  |  | A | C | R | I | I
MoTeC parsers (.ld/.ldx/.svm) |  |  | A | R | C | C | I
Backend platform (FastAPI/ORM/CI) |  |  | A | R | C | C | I
Race Engineering Agent design |  |  | A | R | R | C | I
Clerk JWT / identity & roles |  |  | A | R | C | C | I
RLS / tenant isolation |  |  | A | R | I | C | I
Cost levers (tier/cache/meter) |  |  | A | R | C | C | I
Frontend dashboards |  |  | A | R | C | C | I
Deployment & hosting |  |  | A | R | I | I | I
Billing / Stripe / pricing |  |  | R | C | I | I | A
Acceptance testing (DoD) |  |  | A | C | C | R | I
BizDev / league pilots |  |  | R | I | I | I | A
Corner-dossier content |  |  | A | C | R | C | I
R | Responsible | A | Accountable |  | C | Consulted | I | Informed

## Risk Register
Project | ByteCraft Racing — Race Engineering Manager |  |  |  | Baseline Date |  | 30 Jun 2026
PM | Ohioma
ID | RISK |  |  | CAT | P (1-5) | I (1-5) | Score | Response
R1 | Role gating is client-side only — not trustworthy until Clerk JWT lands |  |  | Technical | 4 | 5 | 20 | Mitigate — Clerk JWT is the critical-path unlock; gate every API route
R2 | Per-run AI cost exposure before revenue exists |  |  | Schedule | 3 | 4 | 12 | Mitigate — telemetry-first launch keeps agent dark until Phase 2
R3 | Heavy users erode margin without an overage layer |  |  | Resource | 3 | 3 | 9 | Mitigate — usage credits priced 3–7× cost
R4 | LMU sim quirks: ambient/track temp channels unreliable |  |  | Technical | 4 | 2 | 8 | Accept — flag explicitly, never hide
R5 | Unverified format assumptions (the .svm guess-vs-reality precedent) |  |  | Technical | 2 | 4 | 8 | Mitigate — no format ships unverified against real files
R6 | Live-coaching cost anchor pollutes premium-tier pricing |  |  | External | 2 | 3 | 6 | Avoid — separate real-time cost from batch inference architecturally
R7 | Repo push blocked by driver PII in real .ld files |  |  | Technical | 3 | 2 | 6 | Mitigate — commit a truncated, anonymized fixture first
R8 | Single-title dependency on Le Mans Ultimate |  |  | External | 2 | 3 | 6 | Accept — stack is title-agnostic; expansion is a parser + reference data
R9 | Competitor funding (Track Titan) / brand (Trophi.ai) |  |  | External | 3 | 3 | 9 | Mitigate — hold the unclaimed 'engineer the car' position
R10 | TimescaleDB hypertable conversion at deploy |  |  | Technical | 2 | 2 | 4 | Accept — deferred until MoTeC ingest activates; low blast radius
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Score | P x I
Response | Avoid | Mitigate | Transfer | Accept
CAT | Technical | Schedule | Resource | External

## Burndown Charts
Project | ByteCraft Racing — Iteration 1 'Wire the spine' (6 stories: S1–S6)
Start | 10 Jul 2026 (est.) |  | End | TBD
Week | Ideal | Actual | Scope Change Notes
1 | 100% | 100% | Baseline = 6 stories remaining (normalized to 1.0). Actual updates weekly once Iteration 1 starts; log scope changes here.
2 | 93.33%
3 | 86.67%
4 | 80%
5 | 73.33%
6 | 66.67%
7 | 60%
8 | 53.33%
9 | 46.67%
10 | 40%
11 | 33.33%
12 | 26.67%
13 | 20%
14 | 13.33%
15 | 6.667%
16 | 0%

## Status Report
Project | ByteCraft Racing — Race Engineering Manager |  |  | Date | 10 Jul 2026
PM | Ohioma
Health | ON TRACK — one watch item (Phase 1 vs agent sequencing) |  | ON TRACK |  | AT RISK |  |  | OFF TRACK
STATUS |  | Phase 0 (prototyping) substantially complete: MoTeC 70-channel decode confirmed against real files; agent prototype v2→v12 running live; cost model + metering (30+ tests); 14-table ORM.
Launch blocker cleared — MoTeC binary decode resolved 30 Jun 2026. Phase 1 is now integration + deployment, not research.
Race Engineering Agent works as a client-side prototype (orchestrator → 6 specialists → optimizer → synthesizer). It goes server-side in Phase 2.
Strategy holds: launch a telemetry product first; keep the agent dark until revenue exists.
NEXT |  | Iteration 1 — 'Wire the spine' (6 INVEST stories):
S1 sanitized .ld fixture → S2 GitHub push
S3 Clerk JWT + role claims (the unlock)
S4 get_db() SET LOCAL RLS; S5 agent server-side
S6 enforce cost levers (tiering / caching / metering)
Then: Phase 1 deploy + TimescaleDB conversion
NEED |  | Provision Clerk (auth), Stripe (billing), hosting (Vercel/Netlify + Railway/Render/Fly)
Production domain + DNS
Decision: plan-tier pricing (Rookie → Paddock) and usage-credit rates
Any additional real LMU session exports for validation
ETA |  | Phase 1 (telemetry launch): once deploy pipeline is green — target date TBD after S1/S2
Phase 2 (agent live + teams): after the identity spine (S3–S6) lands
MILESTONE/RISK | [5 empty] | DUE | STATUS
Sanitized .ld fixture + GitHub push | [5 empty] | Jul 2026 | LATE
Clerk JWT integration (critical path) | [5 empty] | TBD | AT RISK
Phase 1 deploy (hosting + Postgres) | [5 empty] | TBD | ON TRACK
Agent server-side migration | [5 empty] | TBD | ON TRACK
Stripe billing + plan tiers | [5 empty] | TBD | AT RISK

## Kick-Off Document
Project | ByteCraft Racing — Race Engineering Manager |  |  | Date | 10 Jul 2026 (baseline 30 Jun 2026)
PM | Ohioma — PMO / Product Owner, Axiom Black, LLC
PURPOSE - Problem & Intended Value
A sim-racing telemetry + AI race-engineering platform for Le Mans Ultimate (LMU). Every competitor (Track Titan, Trophi.ai, RaceLab, RaceData.AI) coaches the DRIVER. ByteCraft engineers the CAR and the SESSION — an unclaimed market position.
Decode MoTeC .ld/.ldx/.svm telemetry into a full session breakdown, and give the driver an agentic Race Engineer that reasons across aero, tires, powertrain, strategy, environment and KPIs — output no human race engineer would otherwise provide to a sim racer.
Built by Axiom Black, LLC with The ByteCraft Company. Methodology foundation: Clean Agile (INVEST stories, acceptance-test-as-DoD, Iron Cross, ROI triage).
OUTCOMES - SUCCESS CRITERIA
1. A solo driver uploads a matched .ld/.ldx/.svm set and sees a full 70-channel breakdown + cross-session trends (Phase 1 launch).
2. The Race Engineering Agent produces useful, cost-viable engineering guidance server-side (Phase 2).
3. Viable unit economics: ~90% cost reduction vs naive all-Opus baseline via model tiering + prompt caching + run metering.
4. Trustworthy multi-tenant foundation: solo + garages (2–50 seats) isolated at the database layer.
5. Guiding principle: every phase leaves the product in a state a real driver would pay for.
IN SCOPE |  |  |  | OUT OF SCOPE
LMU as launch title; telemetry ingest + dashboard; trend/progression view |  |  |  | AI agent exposure at Phase 1 launch (built, but dark until revenue exists)
Race Engineering Agent (orchestrator → specialists → optimizer → synthesizer) |  |  |  | Additional sim titles — iRacing / ACC (Phase 4 expansion)
Roles (driver/garage-admin/product-admin), garages, quotas, metering, billing |  |  |  | Live on-track / voice coaching (future premium tier, priced separately)
MoTeC parsing (.ld binary, .ldx XML, .svm setup); corner-dossier guide system |  |  |  | Native mobile application
Server-side agent orchestration, prompt caching, cost-lever enforcement |  |  |  | Setup marketplace, public profiles, leaderboards (later platform features)
STAKEHOLDERS & RESPONSIBILITY
NAME |  | ROLE | RESPONSIBILITY |  |  | CADENCE
Ohioma |  | PMO / Product Owner | Product + engineering decisions; accountable for delivery |  |  | Continuous
The ByteCraft Company |  | Development partner | Builds and ships the platform |  |  | Weekly
Claude (Anthropic API) |  | AI build + runtime | Agent orchestration engine; build assistance |  |  | Per session / per run
Axiom Black, LLC |  | Sponsor / parent | Approves scope, budget, brand |  |  | Milestone reviews
TO DO - CONSULTANT
Create sanitized/anonymized .ld test fixture; commit repo & push to GitHub
Integrate Clerk JWT with role claims; enforce role gating at every API route
Wire get_db() SET LOCAL tenant context; activate row-level security policies
Migrate agent orchestration server-side; write per-run cost to agent_runs
Enforce three cost levers: model tiering, prompt caching, run metering
TO DO - CLIENT
Provision accounts: Clerk (auth), Stripe (billing), hosting (Vercel/Netlify + Railway/Render/Fly)
Register production domain; configure DNS
Finalize plan-tier pricing (Rookie → Paddock) and usage-credit rates (3–7× cost)
Decide Phase 1 launch date after deploy pipeline is green
Supply any additional real LMU session exports for validation

## WBS
Project | ByteCraft Racing — Race Engineering Manager |  |  |  | 10 Jul 2026
PM | Ohioma
WBS | WORK PACKAGE / TASK |  |  |  |  | OWNER | HRS | STATUS
1 | Telemetry Ingest |  |  |  |  | ByteCraft |  | DONE
1.1 | .ld binary parser (70 channels) |  |  |  |  | ByteCraft |  | DONE
1.2 | .ldx XML parser (lap + setup, truncation) |  |  |  |  | ByteCraft |  | DONE
1.3 | .svm setup parser (INI, VE vs Fuel) |  |  |  |  | ByteCraft |  | DONE
1.4 | Sanitized test fixture |  |  |  |  | ByteCraft |  | LATE
2 | Backend Platform |  |  |  |  | ByteCraft |  | ACTIVE
2.1 | FastAPI + async SQLAlchemy |  |  |  |  | ByteCraft |  | DONE
2.2 | 14-table ORM (identity/tenancy/sessions/TS) |  |  |  |  | ByteCraft |  | DONE
2.3 | Metering service (3 cost levers) |  |  |  |  | ByteCraft |  | DONE
2.4 | RLS tenant-isolation SQL |  |  |  |  | ByteCraft |  | ACTIVE
2.5 | Docker Compose + GitHub Actions CI |  |  |  |  | ByteCraft |  | DONE
3 | Identity & Tenancy |  |  |  |  | ByteCraft |  | HOLD
3.1 | Clerk JWT + role claims |  |  |  |  | ByteCraft |  | HOLD
3.2 | get_db() SET LOCAL tenant context |  |  |  |  | ByteCraft |  | HOLD
3.3 | Garage seats + invite flow |  |  |  |  | ByteCraft |  | HOLD
4 | Race Engineering Agent |  |  |  |  | Claude/ByteCraft |  | ACTIVE
4.1 | Orchestrator + Synthesizer |  |  |  |  | Claude |  | DONE
4.2 | Specialists: aero/tire/powertrain/tel/strat/env |  |  |  |  | Claude |  | DONE
4.3 | Optimizer (KPI generation) |  |  |  |  | Claude |  | DONE
4.4 | Server-side migration |  |  |  |  | ByteCraft |  | HOLD
4.5 | Model tiering + prompt caching + metering |  |  |  |  | ByteCraft |  | ACTIVE
5 | Frontend |  |  |  |  | ByteCraft |  | ACTIVE
5.1 | Session upload + telemetry viewer |  |  |  |  | ByteCraft |  | DONE
5.2 | Driver dashboard (v12 merged) |  |  |  |  | ByteCraft |  | DONE
5.3 | Trend / progression view |  |  |  |  | ByteCraft |  | ACTIVE
5.4 | Garage + admin dashboards |  |  |  |  | ByteCraft |  | HOLD
5.5 | Corner-dossier guide system |  |  |  |  | Ohioma |  | HOLD
6 | Billing & Pricing |  |  |  |  | Ohioma |  | HOLD
6.1 | Stripe plan tiers (Rookie → Paddock) |  |  |  |  | Ohioma |  | HOLD
6.2 | Usage credits (3–7× cost) |  |  |  |  | Ohioma |  | HOLD
6.3 | Quota enforcement + upgrade path |  |  |  |  | ByteCraft |  | HOLD
7 | Deployment & Ops |  |  |  |  | ByteCraft |  | HOLD
7.1 | Hosting (frontend + backend + Postgres) |  |  |  |  | ByteCraft |  | HOLD
7.2 | TimescaleDB hypertable |  |  |  |  | ByteCraft |  | HOLD
7.3 | Monitoring (Sentry) |  |  |  |  | ByteCraft |  | HOLD
STATUS | ACTIVE | DELAY | HOLD | LATE

## FBS
Project | ByteCraft Racing — Race Engineering Manager |  |  |  | 10 Jul 2026
PM | Ohioma
FEATURE |  |  | SUB FEATURE/CAPABILITY |  |  | USER VALE | MoSCoW | STATUS
Telemetry Dashboard |  |  | 70-channel breakdown + traces |  |  | See exactly what the car did | Must | Prototyped
|  |  | Setup sheet view (.svm) |  |  | Cause behind the telemetry effect | Must | Prototyped
|  |  | Unreliable-channel flagging |  |  | Honest data (ambient/track temp) | Must | Done
Session History |  |  | Saved sessions per user |  |  | Keep and revisit past runs | Must | Planned
Trend / Progression |  |  | Best-lap + consistency across sessions |  |  | Prove you are improving | Must | Prototyped
|  |  | Car-level filter dimension |  |  | Compare within a class | Could | Backlog
Race Engineering Agent |  |  | Orchestrated specialist agents |  |  | Engineer the car, not coach driver | Must (P2) | Prototyped
|  |  | Modes: brief / debrief / monitor |  |  | Right analysis for the moment | Should | Prototyped
|  |  | KPI Optimizer + Synthesizer |  |  | Actionable trade-offs | Should | Prototyped
|  |  | Server-side + metered runs |  |  | Cost-safe at scale | Must (P2) | Hold
Corner Dossiers |  |  | One-page-per-corner guides |  |  | Scannable track mastery | Should | Planned
Garages / Teams |  |  | Pooled quota, invite, admin |  |  | Team-level engineering | Must (P2) | Prototyped
Roles |  |  | driver / garage-admin / product-admin |  |  | Right access per user | Must (P2) | Client-side only
Billing |  |  | Plan tiers + Stripe |  |  | Turn usage into revenue | Must (P2) | Planned
|  |  | Usage credits (overage layer) |  |  | Convert heavy users to revenue | Should | Backlog
Live / Voice Coaching |  |  | Real-time on-track |  |  | Premium differentiation | Won't (now) | Future tier
Multi-sim |  |  | iRacing / ACC ingest |  |  | Grow addressable market | Won't (now) | Phase 4
STATUS | ACTIVE | DELAY | HOLD | LATE